## L10 Dashboard
L10 Leadership Meeting
x | Meeting Header
| Meeting Date | 2026-05-01 |  |  | Week Of | 2026-04-27
| Quarter | Q2 2026 |  |  | Facilitator
| Scribe |  |  |  | Timekeeper
| Start Time |  |  |  | End Time
x | Live Meeting Pulse
| Scorecard Health |  | Rock Health |  | To-Do Health |  | Issues Health
| Total Measurables | 2 | Active Rocks | 2 | Open To-Dos | 1 | Open Issues | 1
| Green This Week | 0 | On Track | 2 | Overdue | 0 | Priority 1 | 1
| Red This Week | 0 | Off Track | 0 | Done This Period | 0 | Solved Total | 0
| Missing Updates | 2 | Done | 0 | Rollover 2+ | 0 | Aged 30+ Days | 1
x | Agenda
| Agenda Item | Planned Min | Actual Min | Status | Notes
| Segue | 5
| Scorecard | 5
| Rock Review | 5
| Customer/Employee Headlines | 5
| To Do List | 5
| IDS | 60
| Conclude | 5
| Total | 90 | 0 | Over / Under
x | Segue
| Person | Personal Good News
Arthur Mielnik
Add name here
Add name here
Add name here
Add name here
Add name here
x | Current Week Headlines
| Type | Good/Bad | Headline
x | Conclude: Cascading Messages
| Message |  |  |  | Sent?
x | Conclude: Decisions Made
Decision
x | Conclude: Meeting Ratings (1 to 10)
| Team Member | Rating | Comment
Arthur Mielnik
Add name here
Add name here
Add name here
Add name here
Add name here
Average Rating
x | x | x | x | x | x | x | x | x

## Scorecard
Scorecard
Really important:
1) | Every measurable has exactly one owner.
2) | Every measurable has a clear weekly target.
3) | No discussion during Scorecard review. Send red items to IDS
4) | Missing data is treated as red unless leadership agrees otherwise.
5) | Red 2+ weeks in a row signals a systemic issue.
Metric ID | Category | Measurable | Definition | Owner | Data Source | Frequency | Metric Type | Target Type | Target Value | Upper Target | Unit | 2/2 | 2/9 | 2/16 | 2/23 | 3/2 | 3/9 | 3/16 | 3/23 | 3/30 | 4/6 | 4/13 | 4/20 | 4/27 | Current Week Actual | Current Status | Red Streak | Notes | Push to IDS | IDS Created?
SC-001 | Admissions | New student starts (weekly) | Number of new students who began services this week | Arthur Mielnik | iBRAIN CRM | Weekly | Lagging | Greater Than or Equal To | 2 |  | count | [14 empty] | Missing
SC-002 | Operations | Session note completion rate | % of session notes completed within 48 hours | Arthur Mielnik | Provider dashboard | Weekly | Leading | Greater Than or Equal To | 0.95 |  | % | [14 empty] | Missing

## Rocks
Quarterly Rocks
Rock ID | Quarter | Rock Description | Owner | Type | Department | Success Criteria | Start Date | Due Date | Status | Confidence | Last Update | Blocker | Push to IDS | Date Completed | Notes
R-001 | Q2 2026 | Launch DC clinic admissions pipeline | Arthur Mielnik | Company Rock | Washington DC | First 5 DC students enrolled and active by 6/30/2026 | 2026-04-01 | 2026-06-30 | On Track | Medium | OSSE COA paperwork submitted 4/15 |  | No
R-002 | Q2 2026 | Ship CRM redesign Phase 1 to production | Arthur Mielnik | Company Rock | Technology | All 62 dev workbook tasks closed and CRM live for full team | 2026-04-01 | 2026-06-30 | On Track | High | Mike Reed team on track |  | No

## To-Dos
To-Do List
To-Do ID | Done | To-Do Item | Owner | Date Added | Due Date | Days Open | Status | Source | Source Issue ID | Completed Date | Rollover Count | Push to IDS | Notes
TD-001 | FALSE | Draft revised admissions intake checklist and circulate to leadership | Arthur Mielnik | 2026-04-29 | 2026-05-06 | 2 | Pending | Leadership |  |  | 0 | No
Formulas:
Days Open = IF([Date Added]="","",IF([Completed Date]<>"",[Completed Date]-[Date Added],TODAY()-[Date Added]))

## Issues
Issues (IDS)
Issue ID | Priority | Issue Description | Issue Type | Source | Source ID | Added By | Owner | Date Added | Age (days) | Status | Root Cause | Resolution/Decision | To-Do Created? | Cascading Msg? | Notes
I-001 | 1 | Session note completion lagging across Manhattan team | Process | Scorecard | SC-003 | Arthur Mielnik | Patrick Donohue | 2026-04-29 | 2 | Open |  |  | No | No
Formulas:
Age (days) = IF([Date Added]="","",TODAY()-[Date Added])

## Headlines
Headlines
Headline ID | Date | Type | Good/Bad | Headline | Added By | Needs IDS? | Issue Created? | Notes

## Meeting Archive
Meeting Archive
Meeting Date | Facilitator | Scribe | Attendees | Absent | Scorecard Red Count | Off-Track Rocks | To-Dos Reviewed | To-Dos Completed | To-Do Completion Rate | Issues Solved | Issues Remaining | Cascading Messages | Key Decisions | Meeting Rating Avg | Rating Notes

## Leadership Rollup
Leadership Rollup
Person | Seat / Role | Scorecard Owned | Red Metrics | Rocks Owned | Off-Track Rocks | Open To-Dos | Overdue To-Dos | Open Issues
Arthur Mielnik | Strategic Planning | 2 | 0 | 2 | 0 | 1 | 0 | 0
Add name here | Role | 0 | 0 | 0 | 0 | 0 | 0 | 0
Add name here | Role | 0 | 0 | 0 | 0 | 0 | 0 | 0
Add name here | Role | 0 | 0 | 0 | 0 | 0 | 0 | 0
Add name here | Role | 0 | 0 | 0 | 0 | 0 | 0 | 0
Add name here | Role | 0 | 0 | 0 | 0 | 0 | 0 | 0
Add name here | Role | 0 | 0 | 0 | 0 | 0 | 0 | 0
Add name here | Role | 0 | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
Overdue To-Dos = IF([Person]="","",SUMPRODUCT(('To-Dos'!D3:D52=[Person])*('To-Dos'!H3:H52<>"Done")*('To-Dos'!F3:F52<>"")*('To-Dos'!F3:F52<TODAY())))

## Settings
Settings and Dropdowns
Leadership Team |  |  |  | Quarter Setup |  |  | Dropdown Lists
Name | Seat / Role | Email | Active? | Quarter | Start Date | End Date | Scorecard Categories | Target Types | Rock Statuses | To-Do Statuses | Issue Statuses | Issue Sources | Issue Types | Headline Types | Rock Types | Departments | Confidence Levels | Yes/No | Good/Bad | Reporting Frequency | Priority | Source Categories
Arthur Mielnik | Strategic Planning | arthur@ibrain.org | Yes | Q1 2026 | 2026-01-01 | 2026-03-31 | Finance | Greater Than or Equal To | On Track | Pending | Open | Scorecard | Problem | Customer | Company Rock | Manhattan | High | Yes | Good | Weekly | 1 | Scorecard
Add name here | Role | email@ibrain.org | Yes | Q2 2026 | 2026-04-01 | 2026-06-30 | Operations | Greater Than | Off Track | Done | IDS Selected | Rock | Idea | Employee | Department Rock | Brooklyn | Medium | No | Bad | Monthly | 2 | Rock
Add name here | Role | email@ibrain.org | Yes | Q3 2026 | 2026-07-01 | 2026-09-30 | Clinical | Less Than or Equal To | Done | Dropped | Solved | To-Do | Question | Operational | Individual Rock | Washington DC | Low |  | Neutral | Quarterly | 3 | Headline
Add name here | Role | email@ibrain.org | Yes | Q4 2026 | 2026-10-01 | 2026-12-31 | HR | Less Than | Dropped | Converted to Issue | Parked | Customer Headline | Risk | Vendor |  | Cross-site |  |  |  |  | Later | Leadership
Add name here | Role | email@ibrain.org | Yes |  |  |  | Compliance | Equal To |  |  | Archived | Employee Headline | Opportunity | Other |  | Finance |  |  |  |  | Parked | Other
Add name here | Role | email@ibrain.org | Yes |  |  |  | Admissions | Between |  |  |  | Leadership Observation | People |  |  | HR
Add name here | Role | email@ibrain.org | Yes |  |  |  | Marketing | Yes / No |  |  |  | External | Process |  |  | Clinical
Add name here | Role | email@ibrain.org | Yes |  |  |  | Technology | Completed / Not Completed |  |  |  | Other | Customer |  |  | Operations
[7 empty] | Fundraising | [5 empty] | Financial |  |  | Technology
[7 empty] | Other | [5 empty] | Compliance |  |  | Other

## Archives
Archives- (Closed out To do's issues, rocks and headlines)
Archive Type | Original ID | Description | Owner | Date Added | Date Closed | Final Status | Notes